## Capital Acquisition
Pursuant to IC 20-40-18-6, the North Newton School Corporation plan contains a listing of all proposed capital expenditures that exceed $10,000 that are expected to be acquired within the three years immediately following the year the plan was adopted.
| Capital Project Plan Adoption Date: | 2024-11-01
| Asset Description* |  | Acquisition Amount
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
Note: The description may include a physical description of the asset and/or any applicable make, model, manufacturer,
or VIN Number if applicable.
Additional sheets may be added if necessary

## Projects Capital in Nature
Pursuant to IC 20-40-18-6, the North Newton School Corporation plan contains a listing of all proposed projects that are capital in nature that exceed $10,000 that are expected to begin within the three years immediately following the year the plan was adopted.
| Capital Project Plan Adoption Date: |  | 2025-09-24
| Project Description* | Estimated Start Date | Estimated End Date | Estimated Project Cost
1 | Paint- all buildings | 2026-06-01 | 2026-08-01 | 36750
2 | Security upgrades - all buildings | 2026-06-01 | 2026-08-01 | 75000
3 | Flooring- Lincoln Media Center | 2026-06-01 | 2026-08-01 | 11550
4 | LED Upgrade - NN Jr/Sr High | 2026-01-05 | 2026-08-01 | 700000
5 | Flooring - all buildings | 2026-06-01 | 2026-08-01 | 21000
6 | Plumbing/ restroom upgrades/ ADA - Lincoln | 2026-06-01 | 2026-08-01 | 78750
7 | Playground Upgrade/ADA - all elementary schools | 2026-06-01 | 2026-08-01 | 275000
8 | Windmill Upgrade & Repair | 2026-01-05 | 2026-03-01 | 65000
9 | Gym Restroom Renovation/ADA - Morocco | 2026-06-01 | 2026-08-01 | 60000
10 | Flooring - all buildings | 2026-06-01 | 2026-08-01 | 21000
11 | Locker Room upgrade/Restroom Renovation/ADA- North Newton Jr/Sr HS | 2026-06-01 | 2026-08-01 | 750000
12 | Paint - all buildings | 2026-06-01 | 2026-08-01 | 36750
13 | Sidewalk Repair - Lake Village | 2026-06-01 | 2026-08-01 | 40000
14 | Rework Chilled Water System - Jr./Sr. High | 2026-06-01 | 2026-08-01 | 200000
15 | Replace Welding Shop Airhandling Units - Jr./Sr. High | 2026-06-01 | 2026-08-01 | 275000
16 | Roof Replacement - Lake Village | 2026-06-01 | 2026-08-01 | 750000
17 | Commercial Kitchen Upgrade FACS Room - NN Jr/Sr High | 2026-06-01 | 2026-08-01 | 400000
18 | Science Lab Renovations - NN Jr/Sr High | 2026-06-01 | 2026-08-01 | 800000
19 | Restroom Renovation / Lake Village | 2026-06-01 | 2026-08-01 | 50000
20 | Tree Removal - Lincoln | 2026-06-01 | 2026-08-01 | 10000
21 | Vertical Roof Panel Replacement - Lincoln | 2026-06-01 | 2026-08-01 | 100000
22 | Baseball / Softball / Football Complex Redesign - NN Jr/Sr High | 2026-06-01 | 2026-08-01 | 3000000
23 | Swimming Pool Repair | 2026-06-01 | 2026-08-01 | 200000
23 | Generator Installation - Lake Village | 2026-06-01 | 2026-08-01 | 80000
Additional sheets may be added if necessary

## CP Resolution Template
RESOLUTION TO ADOPT THE CAPITAL PROJECTS FUND PLAN Budget Year 2025
This resolution is adopted by the Board of Trustees of the School Corporation below:
| School Corporation Name: | North Newton School Corporation
| County: | Newton County
WHEREAS, A Capital Project Plan has been established; and
WHEREAS, the Board of Trustees is required under IC 20-40-18-6 to adopt a plan for the Capital Project Plan; and
WHEREAS, the Board of Trustees held a public hearing on the plan date and place below:
| Meeting Date: | 2025-09-24
| Meeting Location: | 310 S Lincoln St, Board Room
THEREFORE, BE IT RESOLVED, by the Board of Trustees that the plan entitled "2025 Capital Project Plan" this resolution, and is adopted as the Board of Trustees' Plan with respect to the Capital Project Plan.
BE IT FURTHER RESOLVED, that the Board of Trustees shall submit a certified copy of this resolution to the Department of Local Government Finance as required by IC 20-40-18-6.
| Adoption Date: | 2025-09-24
| AYE |  | NAY
| Attest: |  | Secretary of Board of School Trustees